International School

# Capstone Project 2

CMU-SE 451

Sprint Backlog Document

Version 1.3

Date: 12/04/2023

Ticket booking and schedule tracking system

Submitted by C2SE.34

Nguyen Thi My Trinh

Nguyen Huu Huy

Huynh Viet Bao

Nguyen Van Do

Tran Hung Viet

Approved by

Thuan, Nguyen Tan, PhD

Review Panel Representative:

Name	Signature	Date

Capstone Project 2- Mentor:

Name	Signature	Date

PROJECT INFORMATION

PROJECT INFORMATION

| Project Acronym | TSBooking |  |  |
| --- | --- | --- | --- |
| Project Title | Ticket Booking and Schedule Tracking System |  |  |
| Start Date | March 10, 2023 | End Date | May 25, 2023 |
| Lead Institution | International School, Duy Tan University |  |  |
| Project Mentor | MSC, Thuan, Nguyen Tan Email: thuannt.it.dtu@gmail.com Tel: 0905626276 |  |  |
| Scrum Master / Project Leader & contact details | Do, Nguyen Van Email: donguyen2801@gmail.com Tel: 0392219299 |  |  |
| Partner Organization | Duy Tan University |  |  |
| Project Web URL |  |  |  |
| Team Members | Name | Email | Tel |
| 24201208432 | Trinh, Nguyen Thi My | nguyenthimytrinh1610@gmai.com | 0378343128 |
| 2321122721 | Huy, Nguyen Huu | huynguyen291098@gmail.com | 0905067246 |
| 25211203997 | Bao, Huynh Viet | baohuynhviet145@gmail.com | 0795537477 |
| 25211603690 | Viet, Tran Hung | thviet2001@gmail.com | 0935361065 |

SPRINT BACKLOG DOCUMENT

| Document Title | Sprint Backlog Document |  |  |
| --- | --- | --- | --- |
| Reporting Period |  |  |  |
| Author(s) & Project | Scrum Master |  |  |
| Team Information | Name |  | Role |
|  | Nguyen Thi My Trinh |  | Member |
|  | Huynh Viet Bao |  | Member |
|  | Nguyen Huu Huy |  | Member |
|  | Tran Hung Viet |  | Member |
|  | Nguyen Van Do |  | Member |
| Date |  | Filename | Sprint_Backlog_V1.3.docx |
| Access |  |  |  |

DOCUMENT HISTORY

| Version | Date | Comments |
| --- | --- | --- |
| V1.0 | 07/04/2023 | Create Sprint Backlog Sprint 1 |
| V1.1 | 08/04/2023 | Update Sprint Backlog Sprint 1 |
| V1.2 | 08/04/2023 | Update Sprint Backlog Sprint 2 |
| V1.3 | 12/04/2023 | Update Sprint Backlog Sprint 3 |

DOCUMENT APPROVALS

The following signatures are required for approval of this document.

| MSC, Thuan, Nguyen Tan Mentor |  | Date |
| --- | --- | --- |
| Do, Nguyen Van Scrum master |  | Date |
| Trinh, Nguyen Thi My Product Owner |  | Date |
| Huy, Nguyen Huu Dev Team |  | Date |
| Bao, Huynh Viet Dev Team |  | Date |
| Viet, Tran Hung Dev Team |  | Date |

TABLE OF CONTENTS

1.	Sprint 1	5

2.	Sprint 2	8

3.	Sprint 3	11

# Sprint 1

| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sprint Planning Meeting | All members | Done | 16 | 21/02/2023 | 21/02/2023 |
| 2 | Create Backlog Document for Sprint 1 | Do | Done | 4 | 22/02/2023 | 22/02/2023 |
| 3 | Create Test Plan Document for Sprint 1 | Huy | Done | 4 | 23/02/2023 | 23/02/2023 |
| 4 | Create Database Document Sprint 1 | Bao | Done | 4 | 24/02/2023 | 24/02/2023 |
| 5 | Design UI |  |  |  |  |  |
| 6 | Design UI of “Login/Logout” | Viet | Done | 8 | 25/02/2023 | 25/02/2023 |
| 7 | Design UI of “Homepage” | Huy | Done | 8 | 26/02/2023 | 26/02/2023 |
| 8 | Review all UI of Sprint 1 | All member | Done | 16 | 27/02/2023 | 27/02/2023 |
| 9 | Design Test Case | Trinh | Done | 4 | 28/02/2023 | 28/02/2023 |
| 10 | Coding |  |  |  |  |  |
| 11 | Code front-end of “Login” | Viet | Done | 12 | 01/03/2023 | 02/03/2023 |
| 12 | Code back-end of “Login” | Bao | Done | 12 | 03/03/2023 | 04/03/2023 |
| 13 | Code front-end of “Logout” | Huy | Done | 12 | 05/03/2023 | 06/03/2023 |
| 14 | Code back-end of “Logout” | Do | Done | 12 | 07/03/2023 | 08/03/2023 |
| 15 | Code front-end of “Homepage” | Bao | Done | 20 | 09/03/2023 | 11/03/2023 |
| 16 | Code back-end of “Homepage” | Do | Done | 12 | 12/03/2023 | 13/03/2023 |
| 17 | Testing | Trinh | Done | 8 | 14/03/2023 | 15/03/2023 |
| 18 | Fix bugs | Huy,Viet | Done | 32 | 16/03/2023 | 17/03/2023 |
| 19 | Re-Testing | Bao | Done | 4 | 18/03/2023 | 18/03/2023 |
| 20 | Fix bugs of Sprint 1 | Do, Trinh | Done | 24 | 19/03/2023 | 20/03/2023 |
| 21 | Release Sprint 1 |  |  |  |  |  |
| 22 | Sprint 1 Review Meeting | All member | Done | 16 | 21/03/2023 | 21/03/2023 |
| 23 | Sprint 1 Retrospective | All member | Done | 32 | 22/03/2023 | 22/03/2023 |

| No. | Hours available per Sprint | Member Name |
| --- | --- | --- |
| 1 | 60 | Nguyen Van Do |
| 2 | 60 | Nguyen Huu Huy |
| 3 | 60 | Huynh Viet Bao |
| 4 | 56 | Tran Hung Viet |
| 5 | 44 | Nguyen Thi My Trinh |

| SPRINT 1 . Summary Table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | 21/02/2023 | 22/02/2023 | 23/02/2023 | 24/02/2023 | 25/02/2023 | 26/02/2023 | 27/02/2023 | 28/02/2023 | 01/03/2023 | 02/03/2023 | 03/03/2023 | 04/03/2023 | 05/03/2023 | 06/03/2023 | 07/03/2023 | 08/03/2023 | 09/03/2023 | 10/03/2023 | 11/03/2023 | 12/03/2023 | 13/03/2023 | 14/03/2023 | 15/03/2023 | 16/03/2023 | 17/03/2023 | 18/03/2023 | 19/03/2023 | 20/03/2023 | 21/03/2023 | 22/03/2023 |
| Estimate | 268 | 252 | 248 | 244 | 236 | 232 | 224 | 208 | 180 | 180 | 180 | 168 | 168 | 148 | 128 | 128 | 128 | 120 | 116 | 112 | 92 | 92 | 84 | 84 | 70 | 56 | 56 | 56 | 48 | 16 |
| Actual | 253 | 241 | 237 | 233 | 226 | 223 | 213 | 207 | 180 | 180 | 182 | 168 | 168 | 150 | 132 | 132 | 130 | 124 | 124 | 120 | 102 | 102 | 94 | 94 | 90 | 78 | 74 | 74 | 64 | 52 |

SPRINT 1 . Summary Table

# Sprint 2

| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sprint Planning Meeting | All member | Done | 16 | 23/03/2023 | 23/03/2023 |
| 2 | Create Backlog Document for Sprint 2 | Bao | Done | 4 | 24/03/2023 | 24/03/2023 |
| 3 | Create Test Plan Document for Sprint 2 | Huy | Done | 4 | 25/03/2023 | 25/03/2023 |
| 4 | Create Database Document for Sprint 2 | Viet | Done | 4 | 26/03/2023 | 26/03/2023 |
| 5 | Design UI |  |  |  |  |  |
| 6 | Design UI of “ Search” | Viet | Done | 4 | 27/03/2023 | 27/03/2023 |
| 7 | Design UI of “View trip” | Trinh | Done | 4 | 28/03/2023 | 28/03/2023 |
| 8 | Design UI of “View travel location” | Bao | Done | 4 | 29/03/2023 | 29/03/2023 |
| 9 | Design UI of " Bus fares" | Do | Done | 4 | 30/03/2023 | 30/03/2023 |
| 10 | Review all UI of Sprint 2 | All member | Done | 16 | 31/03/2023 | 31/03/2023 |
| 11 | Design Test Case | Viet | Done | 4 | 01/04/2023 | 01/04/2023 |
| 12 | Coding |  |  |  |  |  |
| 13 | Code front-end of “ Search ” | Huy | Done | 8 | 02/04/2023 | 03/04/2023 |
| 14 | Code back-end of “ Search ” | Bao | Done | 8 | 04/04/2023 | 05/05/2023 |
| 15 | Code front-end of “ View trip” | Viet | Done | 8 | 06/04/2023 | 07/04/2023 |
| 16 | Code back-end of “ View trip ” | Trinh | Done | 8 | 08/04/2023 | 09/05/2023 |
| 17 | Code front-end of “ View travel location ” | Do | Done | 8 | 10/04/2023 | 11/04/2023 |
| 18 | Code back-end of “ View rental location ” | Huy | Done | 8 | 12/04/2023 | 13/04/2023 |
| 19 | Code front-end of “ Bus fares ” | Do | Done | 8 | 14/04/2023 | 15/04/2023 |
| 20 | Code back-end of “ Bus fares ” | Huy | Done | 4 | 16/04/2023 | 16/04/2023 |
| 21 | Testing | Bao | Done | 4 | 15/04/2023 | 15/04/2023 |
| 22 | Fix bugs | Trinh,Bao | Done | 8 | 16/04/2023 | 16/04/2023 |
| 23 | Re-Testing | Viet | Done | 4 | 17/04/2023 | 17/04/2023 |
| 24 | Integrate into the Sprint 1 | Do, Viet | Done | 8 | 18/04/2023 | 18/04/2023 |
| 25 | Integration test |  |  |  |  |  |
| 26 | System test | Viet | Done | 4 | 19/04/2023 | 19/04/2023 |
| 27 | Regression Test | Huy | Done | 4 | 20/04/2023 | 20/04/2023 |
| 28 | Fix bugs of Sprint 2 | Trinh, Do | Done | 16 | 20/04/2023 | 22/04/2023 |
| 29 | Release Sprint 2 |  |  |  |  |  |
| 30 | Review Sprint 2 Meeting | All member | Done | 16 | 23/04/2023 | 23/04/2023 |
| 31 | Sprint 2 Retrospective | All member | Done | 16 | 22/04/2023 | 22/04/2023 |

| No. | Hours available per Sprint | Member Name |
| --- | --- | --- |
| 1 | 60 | Nguyen Van Do |
| 2 | 56 | Nguyen Huu Huy |
| 3 | 48 | Huynh Viet Bao |
| 4 | 52 | Tran Hung Viet |
| 5 | 52 | Nguyen Thi My Trinh |

| SPRINT 2 . Summary Table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | 23/03/2023 | 24/03/2023 | 25/03/2023 | 26/03/2023 | 27/03/2023 | 28/03/2023 | 29/03/2023 | 30/03/2023 | 31/03/2023 | 01/04/2023 | 02/04/2023 | 03/04/2023 | 04/04/2023 | 05/04/2023 | 06/04/2023 | 07/04/2023 | 08/04/2023 | 09/04/2023 | 10/04/2023 | 11/04/2023 | 12/04/2023 | 13/04/2023 | 14/04/2023 | 15/04/2023 | 16/04/2023 | 17/04/2023 | 18/04/2023 | 19/04/2023 | 20/04/2023 | 21/04/2023 | 22/04/2023 |
| Estimate | 244 | 228 | 224 | 220 | 216 | 212 | 208 | 204 | 200 | 184 | 172 | 172 | 148 | 148 | 124 | 124 | 116 | 116 | 108 | 92 | 92 | 80 | 80 | 72 | 68 | 48 | 48 | 40 | 40 | 32 | 16 |
| Actual | 292 | 260 | 254 | 256 | 234 | 231 | 226 | 218 | 202 | 185 | 172 | 170 | 148 | 146 | 128 | 128 | 120 | 117 | 108 | 102 | 102 | 91 | 93 | 81 | 77 | 59 | 59 | 55 | 55 | 51 | 31 |

SPRINT 2 . Summary Table

# Sprint 3

| No. | Task | Responsible person | Status | Estimate (hours) | Start Date | End Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sprint Planning Meeting | All members | Done | 16 | 23/04/2023 | 23/04/2023 |
| 2 | Create Sprint 3 Backlog Document | Bao | Done | 4 | 24/04/2023 | 24/04/2023 |
| 3 | Create Test Plan Document for Sprint 3 | Bao | Done | 4 | 25/04/2023 | 25/04/2023 |
| 4 | Create Database Document for Sprint 3 | Do | Done | 4 | 26/04/2023 | 26/04/2023 |
| 5 | Design UI |  | Done |  |  |  |
| 6 | Design UI of “Garage statistics” | Viet | Done | 4 | 28/04/2023 | 28/04/2023 |
| 7 | Design UI of “Send messages to customers” | Huy | Done | 4 | 29/04/2023 | 29/04/2023 |
| 8 | Design UI of “ Report late” | Trinh | Done | 4 | 30/04/2023 | 30/04/2023 |
| 9 | Design UI of “ Reflect customers” | Trinh | Done | 4 | 01/05/2023 | 01/05/2023 |
| 10 | Review all UI of Sprint 3 | All member | Done | 16 | 02/05/2023 | 02/05/2023 |
| 11 | Design Test Case | Bao | Done | 4 | 03/05/2023 | 03/05/2023 |
| 12 | Coding |  | Done |  |  |  |
| 13 | Code front-end of “ Garage statics ” | Do | Done | 8 | 04/05/2023 | 05/05/2023 |
| 14 | Code Back-end of “ Garage statics” | Trinh | Done | 8 | 06/05/2023 | 07/05/2023 |
| 15 | Code front-end of “ Send messages to customers” | Huy | Done | 8 | 08/05/2023 | 09/05/2023 |
| 16 | Code Back-end of “ Send messages to customers” | Trinh | Done | 6 | 10/05/2023 | 10/05/2023 |
| 17 | Code front-end of “ Report late ” | Viet | Done | 6 | 11/05/2023 | 11/05/2023 |
| 18 | Code Back-end of “ Report late” | Trinh | Done | 6 | 12/05/2023 | 12/05/2023 |
| 19 | Code front-end of “ Reeflect customers ” | Huy | Done | 6 | 13/05/2023 | 13/05/2023 |
| 20 | Code Back-end of “ Reeflect customers” | Bao | Done | 6 | 14/05/2023 | 14/05/2023 |
| 21 | Testing | Viet | Done | 6 | 15/05/2023 | 15/05/2023 |
| 22 | Fix bugs | Trinh | Done | 8 | 16/05/2023 | 16/05/2023 |
| 23 | Re-Testing | Huy | Done | 4 | 17/05/2023 | 17/05/2023 |
| 24 | Integrate into the Sprint1 & Sprint2 | Do | Done | 8 | 18/05/2023 | 18/05/2023 |
| 25 | Integration test |  | Done |  |  |  |
| 26 | System test | Huy | Done | 4 | 20/05/2023 | 20/05/2023 |
| 27 | Regression Test | Bao | Done | 4 | 21/05/2023 | 21/05/2023 |
| 28 | Fix bugs of Sprint 3 | Trinh,Viet |  | 8 | 22/05/2023 | 22/05/2023 |
| 29 | Release Sprint3 |  | Done |  |  |  |
| 30 | Sprint 3 Review Sprint 3 | All member | Done | 16 | 23/05/2023 | 23/05/2023 |
| 31 | Sprint 3 Retrospective | All member | Done | 16 | 24/05/2023 | 24/05/2023 |

| No. | Hours available per Sprint | Member Name |
| --- | --- | --- |
| 1 | 44 | Nguyen Van Do |
| 2 | 48 | Nguyen Huu Huy |
| 3 | 44 | Huynh Viet Bao |
| 4 | 44 | Tran Hung Viet |
| 4 | 72 | Nguyen Thi My Trinh |

| SPRINT 3 . Summary Table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | 23/04/2023 | 24/04/2023 | 25/04/2023 | 26/04/2023 | 27/04/2023 | 28/04/2023 | 23/04/2023 | 30/04/2023 | 01/05/2023 | 02/05/2023 | 03/05/2023 | 04/05/2023 | 05/05/2023 | 06/05/2023 | 07/05/2023 | 08/05/2023 | 09/05/2023 | 10/05/2023 | 11/05/2023 | 12/05/2023 | 13/05/2023 | 14/05/2023 | 15/05/2023 | 16/05/2023 | 17/05/2023 | 18/05/2023 | 19/05/2023 | 20/05/2023 | 21/05/2023 | 22/05/2023 | 23/05/2023 |
| Estimate | 228 | 212 | 208 | 204 | 200 | 196 | 192 | 188 | 184 | 168 | 152 | 152 | 132 | 132 | 116 | 116 | 104 | 104 | 100 | 96 | 92 | 84 | 76 | 64 | 64 | 56 | 52 | 40 | 40 | 32 | 16 |
| Actual | 255 | 235 | 219 | 215 | 213 | 211 | 199 | 191 | 181 | 168 | 152 | 152 | 132 | 132 | 116 | 117 | 104 | 104 | 100 | 96 | 92 | 84 | 76 | 64 | 66 | 56 | 52 | 40 | 40 | 32 | 16 |

SPRINT 3 . Summary Table